## Sheet1
NO | Project | APP ID | App Manager / Owner | Architecture | PO Date | PO amount | Project Start time | DEV start time | UAT start time | Dr Drill Time | PRD start time | Handvoer and Closure Time | Status
1 | CDN Solution of China DEP 2025 | APP-39800 | marine.yin@henkel.com | N/A | 2025-02-20 | 21000 | 2025-01-25 | N/A | 2025-01-25 | N/A | 2025-02-28 | 2025-10-22 | Done
2 | China AIGC Application v1 | APP-42327 | heidi.wang@henkel.com | ECI | 2025-03-28 | 30000 | 2025-03-18 | N/A | 2025-03-18 | 2025-04-14 | 2025-04-15 | 2025-06-25 | Done
3 | Scalp check analyzer for SKR_Device 2.0 | App-42272 | yolanda.gan@henkel.com, timtao.li@henkel.com | ECI | 2025-05-19 | 30000 | 2025-05-26 | N/A | 2025-05-26 | 2025-07-07 | 2025-07-08 | 2025-09-02 | Done
4 | Dormakaba | APP-35892 | vince.jiang@henkel.com | N/A | 2025-06-04 | 6000 | 2025-06-12 | N/A | N/A | N/A | 2025-06-12 | 2025-09-02 | Done
5 | Channel Performance Planning | APP-42313 | vanessa.liu@henkel.com | ECI | 2025-07-01 | 27000 | 2025-07-03 | N/A | 2025-07-03 | 2025-08-15 | 2025-08-18 | 2025-10-31 | Done
6 | Beauty Care e-CRM - Mai solution-VSA | APP-39046 | vanessa.liu@henkel.com | N/A | 2025-07-30 | 6000 | 2025-08-05 | N/A | N/A | N/A | 2025-08-05 | 2025-09-19 | Done
7 | Witness Server (IDC) | APP-41309 | desmond.lee@henkel.com | N/A | 2025-10-01 | 18000 | 2025-10-11 | N/A | N/A | N/A | 2025-10-11 | 2025-12-09 | Done
8 | ECHOP FOR HR | APP-40190 | julie.zhai@henkel.com | ASK | 2025-11-04 | 34000 | 2025-10-28 | N/A | 2025-11-04 | N/A | 2025-12-01 | 2025-12-22 | Done
9 | Echop For HCB | APP-42822 | heidi.wang@henkel.com | ASK | 2025-10-30 | 34000 | 2025-10-28 | N/A | 2025-10-28 | 2025-11-26 | 2025-12-01 | 2025-12-22 | Done
10 | DME UAT Separation | APP-38826 | emma.quan@henkel.com | ASK | 2025-11-26 | 36000 | 2025-11-26 | N/A | 2025-11-26 | 2026-03-12 | N/A | 2026-05-22 | Done
11 | DME OPS | APP-38826 | emma.quan@henkel.com | ASK | 2025-12-01 | 27000 | 2025-12-02 | N/A | 2025-12-02 | 2026-03-12 |  |  | Ongoing
12 | CDP add ClickHouse | APP-41603 | will.sun@henkel.com |  | 2025-12-16 | 14000 | 2025-12-16 | N/A | 2025-12-16 | N/A |  | 2026-01-30 | Done
13 | 6Sigma |  |  |  | 2026-05-23 | 39000 | 2026-05-23 | N/A |  |  |  |  | Unstarted
14 | RAQN DEV Env Setup | APP-42247 | yunpeng.kong@henkel.com | ASK | 2026-02-03 | 27000 | 2026-02-27 | 2026-02-27 | N/A | N/A | N/A |  | Ongoing
15 | DME PRD | APP-38826 | emma.quan@henkel.com | ASK | 2026-03-06 | 24000 | 2026-03-09 | N/A | N/A | N/A | 2026-03-09 |  | Ongoing
16 | BECRM | APP-39046 | julie.zheng@henkel.com vanessa.liu@henkel.com rhoda.chen@henkel.com | Self created K8S | 2026-04-09 | 60000 | 2026-04-09 |  | 2026-04-09 |  |  |  | Ongoing